## From Completion Date
Thesis Completion Calculator
from estimated completion date
Note: Winter semester begins Week 1; Summer semester begins approx. Week 18; Fall semester begins approx. Week 36.
Step | Task | Enter approximate week number
1 | Choose estimated COMPLETION DATE (date at which thesis and application to graduate are submitted in Graduate Program Services and all other paperwork is complete, all fees paid, and all accounts settled.) | 36
2 | Allow one week for corrections after the defence date | 35
3 | Your DEFENCE DATE will be this week | 35
4 | Doctoral Thesis: Allow four weeks for review by external examiner and examining committee. Master's Thesis: Allow two weeks for review by the examination committee. | 4
5 | You must therefore have FINAL SIGNOFF FROM YOUR ADVISORY COMMITTEE, an external examiner chosen, and a defence date booked by the end of this week: | 31
6 | Allow a MINIMUM of two weeks for your advisory committee to approve your final draft thesis. | 2
7 | You must therefore have submitted a FINAL DRAFT to your advisory committee not later than the end of this week: | 29
8 | Allow at least a month (4 weeks) for advisory committee comments and corrections on a first draft of your thesis. | 4
9 | You must therefore have a FIRST DRAFT of your thesis to your advisory committee not later than the end of this week: | 25
10 | Allow one day for every three pages of your thesis; usually at least two months; enter number of weeks you estimate for writing. | 8
11 | You must therefore have finished all of your DATA COLLECTION AND ANALYSIS and begin writing your thesis not later than the beginning of this week: | 17
Enter value here:
Enter value here:
Enter value here:
Enter value here:
Enter value here:
Enter value here:

## From Current Date
THESIS COMPLETION CALCULATOR
from current date
Note: One semester equals approximately 17 weeks.
Step | Task | Enter approximate week number
1 | Enter the current week number | 1
2 | Add the number of weeks until your data collection and analysis will be complete | 6
3 | Your DATA COLLECTION AND ANALYSIS will be finished in this week; you can now begin writing your thesis. | 7
4 | Allow one day for every three pages of your thesis; usually at least two months; enter number of weeks you estimate for writing. | 8
5 | Based on this estimate, you should have a FIRST DRAFT of your thesis to your advisory committee not later than the end of this week: | 15
6 | Allow at least a month for advisory committee comments and corrections on a first draft of your thesis. | 4
7 | You should have a FINAL DRAFT of your thesis ready to submit to your advisory committee not later than the end of this week: | 19
8 | Allow a MINIMUM of two weeks for your advisory committee to approve your final draft thesis. | 2
9 | The earliest date at which you should expect to have FINAL SIGNOFF FROM YOUR ADVISORY COMMITTEE, an external examiner chosen, and a defence date booked is the end of this week: | 21
10 | Doctoral Thesis: Allow four weeks for review by external examiner and examining committee. Master's Thesis: Allow two weeks for review by the examination committee. | 4
11 | Your DEFENCE DATE will be this week | 25
12 | Assuming a successful defence, you should allow one week for corrections after the defence date | 1
| Your estimated COMPLETION DATE (date at which thesis and application to graduate are submitted in Graduate Program Services and all other paperwork is complete, all fees paid, and all accounts settled) is the end of this week: | 26
Enter value here:
Enter value here:
Enter value here:
Enter value here:
Enter value here:
Enter value here: